Terms of Reference (ToRs) for the Development of a National Legal Database on Updated Laws and Case Laws Regarding Women's and Girls' Rights.

Consultancy: The consultant will be entrusted with the development of a national legal database on all women’s and girls' rights and updated laws and case laws. This includes research, data compilation, database design, content integration, testing, and feedback collection.

Time Commitment: October 16, 2024 to December 31, 2024

| 2 | # Background |
| --- | --- |

Group Development Pakistan (GDP) is a civil society organization focused on protecting and promoting child rights and Justice with children across Pakistan. With a focus on creating gender-sensitive, inclusive, and child-centric programs, GDP aims to strengthen systems that protect the most vulnerable children and girls from violence and discrimination.

In Pakistan, the legal framework surrounding women's and girls' rights is extensive but often fragmented, making it challenging for stakeholders to access and utilize relevant laws and case law effectively. Establishing a comprehensive national legal database is a beacon of hope, a crucial step towards consolidating these laws, enhancing accessibility, and, most importantly, promoting awareness among legal practitioners, policymakers, and civil society organizations. This will empower them with the necessary information to advocate for women's and girls' rights.

GDP seeks to develop a National Legal Repository on Women’s and Girls' Rights, which will serve as a comprehensive collection of updated laws, policies, and case laws relevant to women's and girls’ rights in Pakistan. This repository will be a key resource for legal practitioners, policymakers, civil society organizations, and researchers involved in promoting and protecting women's and girls' rights, providing them easy access to the most current relevant information.

Initially, this repository will be a physical depository (organized collection of resources) and will not be available digitally. However, the consultant is expected to organize and structure the data to allow for future digital accessibility and user-friendliness.

| 3 | # Objective of the consultancy |
| --- | --- |

Database Development: Our goal is to create a user-friendly, comprehensive, updated national legal database that includes all relevant international instruments, domestic laws, policies, and case laws pertaining to women’s and girls' rights in Pakistan. This database's user-friendly nature, designed with your ease of use in mind, will ensure that stakeholders, including lawyers, judges, policymakers, and activists, can easily navigate it, thereby facilitating their work.

Accessibility: Facilitate easy and timely access to reliable and updated legal information for stakeholders, including lawyers, judges, policymakers, and activists. Through inclusive and intersectional lenses, inform litigation, legal and policy reform, and women/girls-centric programming.

The primary objective of the consultancy is to research, collect, organize, and structure a comprehensive repository of all updated laws, policies, and case laws related to women's and girls’ rights in Pakistan. The consultant will ensure the repository is comprehensive, accessible, and can be easily transitioned into a digital format in the future. Additionally, the consultant will provide guidance on best practices for maintaining and organizing such a repository.

| 3 | # Expected Outcomes |
| --- | --- |

Data Collection: The consultant will utilize various sources, including government publications, legal journals, and online resources, to compile comprehensive legal texts. This process will be transparent and open to scrutiny to ensure the accuracy and reliability of the database.

Testing and Feedback: Conduct user testing sessions on GDP's website with members of the target audience to gather feedback on the database's functionality and content.

A fully functional national legal database accessible to all stakeholders involved in women’s and girls’ rights advocacy.

Increased awareness of women’s and girls’ rights laws among legal practitioners and civil society will lead to a more child-centric and gender-sensitive dispensation of Justice.

Enhanced capacity for legal research related to women and girls’ rights issues to inform legal and policy reform as well as women and girls-centric programming

| 4 | # Scope of Work / Key Responsibilities |
| --- | --- |

The consultant will be responsible for performing the following tasks, including but not limited to:

Research and Data Collection

- Gather and compile all relevant laws, policies, and case laws related to women’s and girls’ rights, including international instruments, constitutional provisions, federal and provincial laws, and case laws.

- Engage with key stakeholders, including government departments, civil society organizations, and legal bodies, to ensure accurate and up-to-date data collection.

- Ensure comprehensive coverage of different jurisdictions (federal and provincial) and identify any recent case laws related to women's rights.

Organizing and Structuring the Repository

- Develop a structured framework for categorizing resources by type of law (statutory, constitutional, case law, administrative), jurisdiction, and year of enactment.

- Ensure the repository is easy to navigate for legal practitioners, researchers, and other stakeholders, ensuring accuracy and completeness.

Collaboration on Database Design

- Work with IT specialists to design a user-friendly interface that supports search functionalities by keywords, categories, and dates, ensuring mobile accessibility.

Stakeholder Engagement

- Collaborate with legal experts, gender-rights activists, and civil society organizations to ensure the repository meets users' needs.

- Facilitate consultations and advisory meetings to gather feedback on the repository's structure, content, and usability.

Recommendations for Future Digital Accessibility

- Develop recommendations for transitioning the repository into a digital format, outlining best practices for data management, accessibility, and sustainability.

- Provide guidance on making the repository user-friendly with suggestions for search functions, categorization tools, and accessibility options, including language inclusion and disability accommodations.

| 5 | # Key Deliverables |
| --- | --- |

Comprehensive Legal Repository:

- The consultant will deliver a well-organized, structured repository of all relevant laws, policies, and case laws concerning women's and girls' rights in Pakistan.

Monthly Progress Reports:

- Regularly submit monthly progress reports detailing ongoing research, data collection, and repository structuring activities, including any challenges and potential recommendations.

Strategic Reports on Intersectionality:

- Provide intersectional analysis using international instruments and frameworks to assess the impact of legal provisions on different groups of women and girls. This should be documented in strategic reports.

| 6 | # Target Audience |
| --- | --- |

- Legal practitioners (lawyers, judges, prosecutors, police)

- Policymakers

- Civil society organizations

- Researchers and academics

| 7 | # Ethical Standards |
| --- | --- |

- The consultant must have completed the UN PSEA online course, which is a prerequisite to ensure a commitment to preventing sexual exploitation and abuse. A certificate of completion must be provided with the proposal for consideration.

| 8 | # Expected Start Date and Duration of Assignment |
| --- | --- |

- The consultancy is expected to start on October 16, 2024, and end on December 31, 2024.

| 9 | # Required Competencies |
| --- | --- |

- Qualifications:

- Minimum Law Graduate (LLB or equivalent) from a recognized university.

- Experience

  - At least two years of experience in legal research, specifically focusing on gender rights, women’s rights, or human rights law.

  - Experience working with a law firm, government departments, international organizations, and civil society on gender and human rights related legal projects is highly desirable.

  - Previous experience in policy review and legislative analysis is a strong asset.

- Skills & knowledge

  - Deep knowledge of Pakistani laws, particularly those related to women’s and girls' rights, including relevant constitutional provisions, and case laws.

  - Strong research and analytical skills, with a demonstrated ability to synthesize complex legal texts.

  - Excellent communication and stakeholder engagement skills, with a proven ability to liaise with various stakeholders, including legal experts, government officials, and civil society.

  - Proficiency in Urdu and English is required; additional language skills (e.g., regional languages) are a plus.

  - Attention to detail and the ability to work independently while adhering to tight deadlines.

  - Knowledge of digital repository management and future scalability strategies would be beneficial, though not mandatory.

  - Core Competencies

  - Able to coordinate and deliver promptly

  - Familiar with excel

| 9 | # Evaluation |
| --- | --- |

User	satisfaction surveys post-soft launch to assess the effectiveness of the database.

Database usage metrics (e.g., number of searches and unique users) will be tracked for ongoing evaluation.

| 10 | # Timeline |
| --- | --- |

| Week: 1+2+3+4+5 | Research and compilation of data | November 15, 2024 |
| --- | --- | --- |
| Week: 6+7 | Database design and initial content integration | November 29, 2024 |
| Week: 8 | Testing phase with feedback collection | Dec 08,2024 |
| Week: 9+10 | Final adjustments based on feedback and official launch | December 24, 2024 |

| 10 | # Reporting |
| --- | --- |

Monthly Progress Reports:

- The consultant will submit detailed monthly progress reports that provide an update on the status of data collection, organization, and repository structuring.

- These reports will also highlight any challenges faced, stakeholder feedback, and adjustments made to the process.

Final Report:

- Upon project completion, the consultant will prepare a comprehensive final report. This report will include:

- A summary of the development process.

- A detailed account of stakeholder consultations and feedback.

- Challenges encountered and solutions implemented.

- Methodology used for the collection and organization of data.

- Recommendations for the future digital accessibility of the repository.

- Best practices for repository maintenance and ongoing updates.

Reporting Structure:

- The consultant will report directly to the Executive Director of Group Development Pakistan.

- Close coordination with the legal and technical teams involved in the project is required throughout the consultancy.

| 10 | # How to Apply |
| --- | --- |

Interested candidates who fit the criteria and can immediately join must submit their CVs, cover letters, and references to hr@gdpakistan.org by October 10, 2024. The subject line should read “Application: Consultancy: Legal Database on Women's and Girls' Rights.” Only shortlisted candidates will be contacted.

This consultancy starts on October 16, 2024, and ends on December 31, 2024. Depending on the project's needs and the consultant's performance, an extension may be possible. Youth are highly encouraged to apply.